## Gantt Chart
C++ CTF AGENT ¦ FRONTIER + BFS + FSM COMPETITION GANTT
Unknown-map exploration + goal control • 19 Oct 2026 – 31 Jan 2027 • proposed 300 person-hours
TOTAL HOURS |  |  | SOFTWARE |  |  | RESEARCH |  |  | JOINT |  |  | AISWARYA |  |  |  | NIRMAL |  |  |  | WORK PACKAGES
300 |  |  | 110 |  |  | 114 |  |  | 76 |  |  | 148 |  |  |  | 152 |  |  |  | 14
SOFTWARE ENGINEERING • AISWARYA |  |  |  | RESEARCH • NIRMAL |  |  |  | JOINT / BUFFER • BOTH |  |  |  | Edit START / DAYS / HOURS in the task table. Colored Gantt bars update automatically in Excel.
14 WORK PACKAGES • PLANNED STARTS, DURATIONS AND EFFORT | [9 empty] | OCT 2026 |  | NOV 2026 |  |  |  |  | DEC 2026 |  |  |  | JAN 2027
WP | Work package | Workstream | Owner | Hours | Start | Finish¹ | Days | Depends on² | Status | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25
WP-01 | Competition requirements & rules | Software Engineering | Aiswarya | 12 | 2026-10-19 | 2026-11-01 | 14 | — | Planned
WP-02 | API, movement outcome & pose checks | Software Engineering | Aiswarya | 14 | 2026-10-26 | 2026-11-15 | 21 | WP-01 | Planned
WP-03 | Map memory & confidence tracking | Software Engineering | Aiswarya | 30 | 2026-11-02 | 2026-12-13 | 42 | WP-02 | Planned
WP-04 | Frontier exploration & safe fallback | Software Engineering | Aiswarya | 24 | 2026-11-23 | 2026-12-27 | 35 | WP-02/03 | Planned
WP-05 | FSM, BFS, flags & opponent response | Software Engineering | Aiswarya | 30 | 2026-12-14 | 2027-01-17 | 35 | WP-03/04 | Planned
WP-06 | Unknown-map literature & hypotheses | Research | Nirmal | 24 | 2026-10-19 | 2026-11-29 | 42 | — | Planned
WP-07 | Competition metrics & experiment design | Research | Nirmal | 18 | 2026-10-26 | 2026-11-29 | 35 | WP-06 | Planned
WP-08 | Held-out maps, harness & baselines | Research | Nirmal | 24 | 2026-11-09 | 2026-12-27 | 49 | WP-02/07 | Planned
WP-09 | Tournament tests & FSM/FBE ablations | Research | Nirmal | 28 | 2026-12-21 | 2027-01-24 | 35 | WP-04/05/08 | Planned
WP-10 | Win-rate, robustness & validity analysis | Research | Nirmal | 20 | 2027-01-11 | 2027-01-31 | 21 | WP-09 | Planned
WP-11 | Schedule, review & competition briefing | Joint | Both | 12 | 2026-10-19 | 2026-11-08 | 21 | — | Planned
WP-12 | Agent integration, opponent tests & QA | Joint | Both | 34 | 2026-12-14 | 2027-01-24 | 42 | WP-04/05 | Planned
WP-13 | Final documentation & research report | Joint | Both | 20 | 2027-01-04 | 2027-01-31 | 28 | WP-10/12 | Planned
WP-14 | Contingency & competition readiness | Joint | Both | 10 | 2027-01-18 | 2027-01-31 | 14 | WP-13 | Planned
TOTAL PLANNED PERSON-HOURS |  |  |  | 300 | [5 empty] | 2026-10-19: All 14 bars use conditional formatting, not pictures; edit Start or Days to reschedule.
MILESTONES & PROJECT DEPENDENCIES
23 Oct 2026 • Week 3 review | [9 empty] | 2026-10-19: Completed milestone date given in slide
30 Oct 2026 • Week 4 strategy decision | [9 empty] | 2026-10-19: Provisional month-level target
Nov 2026 • Unknown-map exploration & baselines | [9 empty] | 2026-10-19: Provisional month-level target
Dec–Jan • Tournament tests & reporting | [9 empty] | 2026-10-19: Provisional month-level target
Critical sequence: Rules & movement checks → trustworthy state → explore → objective/tactical policy → held-out matches → robustness analysis.
¹ Finish date = Start + Days − 1 (calculated). ² Dependencies describe handoffs; tasks overlap by design. Compare only implemented, working builds.
Formulas:
RESEARCH = [Start]+[Days]-1

## Milestones & Guide
FBE + BFS + FSM ¦ MILESTONES & EXCEL GUIDE
Revised from supplied 300-hour chart: unknown competition map + opposing agent. Hours/owners preserved.
Milestone | Period / date | Workstream | Evidence / target
Week 3 review | 2026-10-23 | Joint | Project definition, research plan, initial Gantt presentation
Week 4 approach decision | 2026-10-30 | Joint | Select hybrid exploration-first policy; verify assumptions
Unknown-map baseline | November 2026 | Software + Research | Movement outcome tests, varied hidden maps, memory and exploration prototype
Competition testing | December 2026 | Both | Opponent variants, flag logic, tactical replanning and safety tests
Evaluation & report | January 2027 | Research + Joint | Held-out tournament scores, ablations, confidence/limitations
HOW TO EDIT THE GANTT CHART
1 | Go to the Gantt Chart worksheet; all 14 work packages are in rows 12–25.
2 | Change Start in column F or Days in column H. Finish in column G updates by formula.
3 | Change planned effort in column E. The totals in the header and row 27 recalculate.
4 | Use the Status dropdown in column J to track planning progress.
5 | Colors: Software (blue), Research (purple), Joint (teal); all periods remain provisional.
6 | Do not train/tune on the friend's final competition map; use your own diverse development maps plus hidden held-out maps.
7 | Map dimensions are supplied, but neither absolute coordinates nor movement-success confirmation are guaranteed by the header.
8 | Keep original 300-hour allocation; hours mean person-hours, not hours completed.
PROJECT RESPONSIBILITIES & PLANNED PERSON-HOURS
Workstream | Primary owner | Planned hours
Software Engineering | Aiswarya | 0
Research | Nirmal | 0
Joint | Both | 0
TOTAL |  | 0
DISCLAIMER • 300 hours are planned estimates for the two-person team, not hours already worked or confirmed university requirements.

## Competition Research
COMPETITION RESEARCH ¦ FBE + BFS + FSM ¦ HELD-OUT MAPS
Preliminary choice • safe local fallback • A* optional • no performance results yet
Stage | Question / objective | Suggested method | Evidence to collect | Owner | Gate / dependency
1. Rule audit | What counts as winning? How do pickups, diagonals, tagging/collisions, turns work? | Read host rules and make controlled observations | Rules and API tests | Both | Before flag/opponent logic
2. Baselines | How do random and safe movement behave on diverse unseen maps? | Same starting layouts/turn limits; random, 4-way random, safe agent | Invalid request rate; stability; match result if observable | Nirmal | Match action sets
3. Movement confidence | Did our previous action actually move us? | Compare before/after static cells; test failed movement and ambiguous corridors | Pose-confidence flags; mismatches; examples | Aiswarya | No global mapping until credible
4. Exploration | Which online policy finds useful areas without map prior? | Safe local novelty / confirmed frontier memory; recovery on uncertainty | Discovery proxy/coverage only if measured; dead-end stalls | Both | Memory robust first
5. Objective policy | Can a guarded FSM coordinate flag objectives without assuming pickup success? | FSM EXPLORE→APPROACH→PICKUP→RETURN→DELIVER; only verified transitions | Transition validity; confirmed flag events; recovery decisions | Aiswarya | Flag rules confirmed
6. Opponent response | How should a visible enemy alter choices? | Dynamic occupancy/risk, safe retreat or pursuit only if supported by game mechanics | Win rate, collisions, lost turns, objective progress | Aiswarya | No invented combat rules
7. Routing | Does BFS help reach a known frontier/flag route? Is A* worth testing later? | FBE selects target, BFS finds path; A* only after core is stable | Successful routes, path lengths, latency, node expansions | Both | Known traversable graph
8. Generalization | Does the policy beat different opponents on unseen maps? | Diverse maps; held-out final tests; varying opponents; swap start sides | Wins / total, objective outcomes, crash rate, uncertainties | Nirmal | No leakage of final map
8. FSM ablation | Does FSM improve outcomes vs FBE+BFS with simple objective rules? | Run safe / FBE / FBE+BFS / FBE+BFS+FSM under matched tests | Transition errors; recovery success; win results if observable | Nirmal | Working validated variants only
Research question | Hypothesis to test | Measurement
RQ1: exploration effectiveness | Novelty/frontier hybrid explores more reliably than safe random. | Reachable discovery/goal discovery (only if measurable), stalls
RQ2: robust navigation | Outcome-validated state lowers localization errors. | Mismatch count, recovery rate in blocked/ambiguous moves
RQ3: competition performance | Hybrid scores better than existing baselines on held-out maps. | Match win fraction; report wins/draws/losses
RQ4: opponent handling | Visible-enemy avoidance improves survival/progress under supported rules. | Outcome differences across matched opponents
RQ5: routing tradeoff | Known-grid BFS is enough for small maps; A* may help larger maps. | Path length, node expansions, p95 decision time
Reference / resource | URL
Yamauchi (1997): frontier exploration | https://doi.org/10.1109/CIRA.1997.613851
Korf (1990): real-time heuristic search | https://doi.org/10.1016/0004-3702(90)90054-4
Sturtevant (2012): grid benchmarks | https://movingai.com/benchmarks/grids.html
DeepMind (2019): variable-map CTF multi-agent research | https://deepmind.google/blog/capture-the-flag-the-emergence-of-complex-cooperative-agents/
Rule notes | The Week 2 API contains 8 directions + pickup/put-down, but does NOT verify movement success, exact flag rules or opponent interactions.
Design gate | Do not treat lastAction as movement confirmation. Disable unverified localization-dependent behavior when observations are ambiguous.

## Software Path
SOFTWARE PATH ¦ FRONTIER + BFS + FSM
Owner: Aiswarya • 110 direct hours + 38 shared • implementation gates, not completed results
Stage | Window | WPs | Build / implement | Acceptance gate | Research hand-off
S0 Baseline | Oct 2026 | Existing | Preserve random & safe DLL references | Host loads; baselines unchanged | Exact agent revision
S1 API rules | Oct–Nov | WP-01/02 | Movement outcome, diagonal and flag rules | Only validated host assumptions used | Rule/fixture log
S2 Safe fallback | Nov | WP-02/04 | Known-safe local action, novelty, wait | No invalid blocked/unknown requests | Baseline/fallback data
S3 Pose/map | Nov–Dec | WP-03 | Confidence-aware observation merge | Contradictory state triggers recovery | Pose feasibility evidence
S4 Frontiers | Nov–Dec | WP-04 | Reachable known-floor frontier targets | No unreachable/unknown-as-floor routes | Exploration fixture logs
S5 BFS | Dec–Jan | WP-05 | Known-route shortest-path first action | Known-grid routes unit-tested | Route length/latency logs
S6 FSM | Dec–Jan | WP-05 | Explore/approach/pickup/return/deliver/evade/recover | Verified transition guards | FSM fixture/ablation logs
S7 Integrate/QA | Dec–Jan | WP-12/14 | New hybrid DLL, regression and opponent tests | Valid actions, resets, recovery | Tournament-ready build
S8 A* optional | If time | Optional | Compare trusted-map path search | Does not delay core delivery | Exploratory results if run

## Research Path
RESEARCH PATH ¦ CONTROLLED UNKNOWN-MAP EVALUATION
Owner: Nirmal • 114 direct hours + 38 shared • proposed protocol, not measured findings
Stage | Window | WPs | Research work | Evidence / method | Software dependency
R0 Literature | Oct | WP-06 | Frontiers, online search and benchmarks | Dated reading scope, source vs hypothesis | None
R1 Hypotheses | Oct–Nov | WP-06/07 | H1–H6; priority metrics; fair controls | Predefined metrics, test plan | Observe API limits
R2 Verify rules | Nov | WP-07/08 | Check observable wins/flags and move outcomes | Confirmed event feasibility | S1 API rules
R3 Baselines | Nov–Dec | WP-08 | Repeated random / safe / 4-way control | Comparable logs; count failures | S0–S2
R4 Unit tests | Nov–Dec | WP-08/09 | FBE, BFS and FSM synthetic fixtures | Reachability, transitions, recovery | S3–S6
R5 Ablations | Dec–Jan | WP-09 | Safe vs FBE vs FBE+BFS vs +FSM | Identical maps/opponents where possible | Validated variants
R6 Held-out maps | Jan | WP-09/10 | Unseen layouts and diverse opponents | Win rate only if verifiable; robustness | S7 integration
R7 Analyze/report | Jan | WP-10/13 | Uncertainty, limitations and conclusions | Raw data, validity and figures | All available tests
R8 Optional A* | If time | Optional | BFS vs A* on same trusted grids | Node expansion/latency | S8 if implemented